## Intro
Risk Tool Assessment for VCM projects
Version | v. 1.0, March, 2023
Contact | For questions, suggestions, comments, and troubleshooting please use the Carbon Markets CoP channel on Microsoft Teams or by email (CarbonMarketsCommunityofPractice@tnc.org).
Purpose | This tool aims to help project managers identify risks that could affect carbon projects during the design, implementation, and long-term continuity. This tool also aims to assess the need for mitigation measures when risks are considered high or extreme.
Disclaimer | The value of this tool will depend mainly on the correct identification of risks by the project management team and stakeholders, so it is important to evaluate any possibility, even if considered minimal at some point.
General instructions | List all the potential risks in the tab "Risk Registry," considering all the categories. If no risk is identified in one category, it can be deleted. If more categories are needed, add those as necessary. Assess the likelihood and impact of each risk based on your best knowledge, stakeholder consensus, and/or relevant data/ information when available. The formulas will automatically assess the risk score and if extra steps are needed. Some risks may be related to more than one category. Select the most appropriate category. If more lines (risks) are necessary for a given category, just add a new row and copy the formula from one cell (in the same column) to the newly added cells.
If the final risk score is HIGH or EXTREME, its necessary to identify (columns "I" to "L"): a) causes - the key factors that could lead the risk to materialize b) preventive measures - the activities that could minimize the causes, and therefore the chances of the risk materializing c) impact - what are the negative effects that will occur if this risk materializes d) mitigation activities - in case the risk still turns to materialize, what can be done to reduce the negative effects
The list of preventive actions and mitigation activities should then be incorporated into the carbon project design.
Categories instructions | Project Implementation and design: Consider the risk of the proposed activities not being effective enough to tackle the root causes of the problem. Consider any possible threat to project implementation, such as lack of engagement, major diseases affecting in-person activities, presence of other projects nearby negatively affecting the project, lack of technical capacity for implementation and carrying out the project, and others. Project management: Consider in this section the experience of the management team, the capacity to find partners and staff with experience, the capacity of the management team to solve conflicts, and others.
Project management: Consider in this section the experience of the management team, the capacity to find partners and staff with experience, the capacity of the management team to solve conflicts, and others.
Legal and rights: in this section, consider if land and carbon rights are clearly defined. If not, are the steps to secure ownership clearly defined, or this could be a potential risk to the project? Is there any dispute of rights? Or could be in the future? Can the carbon project interfere with other use rights?
Financial Risk: Considering the fluctuation of market prices, and opportunity cost (projects vs most likely alternative scenario), is there nan up-front funding available? Are the funding sources sufficient for the project in the long term?
Policy and Political risks: consider the risk of changes or implementation of any carbon regulation; changes or inclusion of a domestic carbon trading scheme restricting the market, and the necessity of any government approval for the project (and if this approval is likely to be obtained).
Environmental and biodiversity risks: consider if the project activities may generate any kind of pollution, or affect any specie/plant currently in the area.
Social and community risk: consider the presence of other projects close by that could create social conflicts, any possible social critique due to real or perceived negative impacts from the project, and a decrease of interest from the community due to changes in prices. Also, check, is the community is supportive of carbon projects, and if is there a fair benefit-sharing mechanism in place.
Health, safety, and security: consider if the project activities follow rules and regulations about health, safety, and workers' rights. Is the project area unsafe? Is the project activity in an area with a polluted environment?
Natural disaster: consider the possibility of occurring fire, pests and diseases, extreme weather (such as floodings, land slidings, hurricanes), geological failures, and others, as well as the impact those may have.
Reputational Risk: Consider if the project developer and other project partners have experience and a good reputation. Also, does the project uses an internationally recognized carbon certification and non-controversial methodologies? Were additionality and baseline conservatively assessed?
Others: any risk not included in the above categories.
Carbon Toolkit © 2024 by The Nature Conservancy is licensed under CC BY 4.0

## Risk_matrix
IMPACT
| RISK MATRIX |  | Insignificant | Minor | Moderate | Major | Catastrophic | Impact
|  |  | 1 | 2 | 3 | 4 | 5 | Insignificant | Will cause almost no damage to the project. Likely would cause no revenue loss
LIKELIHOOD | Rare | 1 | 1 | 2 | 3 | 4 | 5 | Minor | May cause measurable damage, but will not impact the capacity of the project moving forward. Could cause a revenue loss lower than 5%
| Unlikely | 2 | 2 | 4 | 6 | 8 | 10 | Moderate | Would cause measurable damage, but will not impact the project significantly. This could cause a revenue loss of 5-25%
| Possible | 3 | 3 | 6 | 9 | 12 | 15 | Major | Has high consequences, and may impact the project's future (delay or stop activities or the entire project). This could cause a revenue loss of 25-50%
| Likely | 4 | 4 | 8 | 12 | 16 | 20 | Catastrophic | It will interrupt the project. Likely would lead to a revenue loss major than 50%
| Almost Certain | 5 | 5 | 10 | 15 | 20 | 25
Likelihood
|  | Risk rating | Inferior Limit | Superior Limit | Final Score |  |  | Rare | Very low chance of occurring, below 5%, or happening more then every 100 years
|  | Low | 1 | 4 | Not an immediate concern, but needs to be addressed |  |  | Unlikely | Low chance of hapening, between 5-20%, or every 100-50 years
|  | Medium | 5 | 9 | Not high-priority, but should be considered to plan around project constrains |  |  | Possible | Not clear if more chance of occurring or not. Chance of occurring between 20-50%, or every 50-25 years
|  | High | 10 | 19 | Can have a negative material effect, and need to be controlled |  |  | Likely | A risk that may happen regularly. Chance of occurring between 50-80%, or every 25-10 years
|  | Extreme | 20 | 25 | High-priority, requires prompt response |  |  | Almost Certain | This risk almost definitely will occur. Chance of occurring above 80%, or at least every 10 years

## Risk_Registry
Risk category | Risk Identified and description | Likelihood | Impact | Risk score |  | Mitigation measures needed? | Mitigation Measures
|  | Choose from the drop-down menu |  |  |  |  | Causes | Preventive actions | Impacts | Mitigation activities
Project Implementation and design
| Example risk: lack of engagement of landowners | Rare | Insignificant | 1 | Low | No, stop and go to next risk
Project management
| Example Risk: management team has limited experience in the region | Possible | Moderate | 9 | Medium | No, stop and go to next risk
Legal and rigths
| Example risk: possible land rights dispute | Unlikely | Catastrophic | 10 | High | Yes, fill the Mitigation Measures columns | • Land tenure in the region is not clearly defined • Informal land title transfer and land grabbing • Lack of clear definition of borders | • Secure land and carbon rights by legal means • Work with the government to train staff and increase capacity to clarify land use disputes • post property borders • Provide technical and legal support for the community | • Carbon rights may be lost or held until the issue is clarified • Community may lose its territory or part of it • Community may leave • Ecossystem degradation continues | • Try to solve disputes amicably • Negotiate any informal agreement into legal documentation • Engage community in government programs
Financial Risk
| Example risk: Decline in credits value | Rare | Moderate | 3 | Low | No, stop and go to next risk
Policy and Political risks
| Example risk: the federal government will introduce a domestic trading scheme | Rare | Catastrophic | 5 | Medium | No, stop and go to next risk
Enviromental and biodiversity risks
| Example risk: Loss of habitat of X aquatic species due to hydrological changes | Unlikely | Moderate | 6 | Medium | No, stop and go to next risk
Social and community risk
| Example risk: community members skeptical of carbon projects | Possible | Moderate | 9 | Medium | No, stop and go to next risk
Health, safety and security
| Example risk: contaminated rivers in project area | Likely | Moderate | 12 | High | Yes, fill the Mitigation Measures columns | • Mining activities nearby polluting local streams • Uncontrolled access in areas • Lack of enforcement and monitoring from local authorities | • Monitor the water quality • Notify regulatory bodies of illegal activities • Post information about the dangers of water contamination | • Workers and the local community may suffer diseases if they drink the water or consume fish • Reduced revenue for Fisherman • Biodiversity and ecosystem loss | • Monitor water quality • Notify the community and workers about any pollution • Provide an alternative source of clean water for consumption
Natural disaster
| Example risk: Fire incidents | Likely | Catastrophic | 20 | Extreme | Yes, fill the Mitigation Measures columns | • Dry season • Campers making firepits in dangerous spots • Lightenings | • Monitor more intensely in the dry season • Instruct campers to not create firepits outside delimited camping sites • Post information about fire risk in key entrances | • Biomass, biodiversity, and ecosystem loss • Emisson of GHG and loss of VCUs • Endanger people's lives • Hurt animals living in the area | • Monitor area with fire towers • Train local staff and community about firefighting • Have appropriated equipment in hand • Notify fire brigades ASAP
Reputational Risk.
| Example risk: standard may suffer media critiques | Unlikely | Moderate | 6 | Medium | No, stop and go to next risk
Others
| Example risk | Rare | Insignificant | 1 | Low | No, stop and go to next risk

## Lists
Likelihood | Likelihood value | Impact | Impact value | Value | Rating
Rare | 1 | Insignificant | 1 | 1 | Low
Unlikely | 2 | Minor | 2 | 2 | Low
Possible | 3 | Moderate | 3 | 3 | Low
Likely | 4 | Major | 4 | 4 | Low
Almost certain | 5 | Catastrophic | 5 | 5 | Medium
|  |  |  | 6 | Medium
|  |  |  | 7 | Medium
|  |  |  | 8 | Medium
|  |  |  | 9 | Medium
|  |  |  | 10 | High
|  |  |  | 11 | High
|  |  |  | 12 | High
|  |  |  | 13 | High
|  |  |  | 14 | High
|  |  |  | 15 | High
|  |  |  | 16 | High
|  |  |  | 17 | High
|  |  |  | 18 | High
|  |  |  | 19 | High
|  |  |  | 20 | Extreme
|  |  |  | 21 | Extreme
|  |  |  | 22 | Extreme
|  |  |  | 23 | Extreme
|  |  |  | 24 | Extreme
|  |  |  | 25 | Extreme