## CM_feasibility_template
Health | Primary Column | Action Type | Actual Status | Assigned To | Predecessors | Start Date | Duration | Due Date | Team | Notes | Priority | % Complete | Expected Status | Check Status | Parent | Row ID | Hierarchy | NameID | Approval? | Flag
check | TNC Feasibility workplan | Phase | In Progress | TBD |  | 2023-12-01 | 81d | 2024-03-22 |  |  |  |  | Upcoming | Ok |  | 1 | 0 | 1
check | Project Overview | Workstream | Upcoming | TBD |  | 2023-12-01 | 9d | 2023-12-13 |  |  |  |  | Upcoming | Ok | TNC Feasibility workplan | 2 | 1
O | Project start | Task | Upcoming | TBD |  | 2023-12-01 | 1d | 2023-12-01 |  |  |  |  | Upcoming | Ok | Project Overview | 3 | 2
O | Kick-off meeting | Milestone | Upcoming | TBD | 3 | 2023-12-01 | 0 | 2023-12-01 |  |  |  |  | Upcoming | Ok | Project Overview | 4 | 2
O | Gather information for area characterization | Task | Upcoming | TBD | 4 | 2023-12-04 | 8d | 2023-12-13 |  |  |  |  | Upcoming | Ok | Project Overview | 5 | 2
O | Draft activity plan and theory of change | Task | Upcoming | TBD | 4 | 2023-12-04 | 6d | 2023-12-11 |  |  |  |  | Upcoming | Ok | Project Overview
O | Review available data and needs | Task | Upcoming | TBD | 4 | 2023-12-04 | 5d | 2023-12-08 |  |  |  |  | Upcoming | Ok | Project Overview
O | Risk Analysis | Task | Upcoming | TBD | 4 | 2023-12-04 | 5d | 2023-12-08 |  |  |  |  | Upcoming | Ok | Project Overview
check | Land Tenure and policy | Workstream | Upcoming | TBD | 4 | 2023-12-04 | 15d | 2023-12-22 |  |  |  |  | Upcoming | Ok | TNC Feasibility workplan
O | Review of land tenure and carbon rights | Task | Upcoming | TBD |  | 2023-12-04 | 3d | 2023-12-06 |  |  |  |  | Upcoming | Ok | Land Tenure and policy
O | Review of National and local legislation | Task | Upcoming | TBD |  | 2023-12-04 | 10d | 2023-12-15 |  |  |  |  | Upcoming | Ok | Land Tenure and policy
O | Review Article 6 status in country | Task | Upcoming | TBD |  | 2023-12-04 | 10d | 2023-12-15 |  |  |  |  | Upcoming | Ok | Land Tenure and policy
O | Prepare legal agreements | Task | Upcoming | TBD | 10, 11, 12 | 2023-12-18 | 5d | 2023-12-22 |  |  |  |  | Upcoming | Ok | Land Tenure and policy
O | Make interactions with government officials | Task | Upcoming | TBD |  | 2023-12-04 | 10d | 2023-12-15 |  |  |  |  | Upcoming | Ok | Land Tenure and policy
check | Stakeholder and social safeguards | Workstream | Upcoming | TBD | 4 | 2023-12-04 | 28d | 2024-01-10 |  |  |  |  | Upcoming | Ok | TNC Feasibility workplan
O | Gather information about possible stakeholders | Task | Upcoming | TBD |  | 2023-12-04 | 5d | 2023-12-08 |  |  |  |  | Upcoming | Ok | Stakeholder and social safeguards
O | Stakeholder identification plan | Task | Upcoming | TBD | 16 | 2023-12-11 | 3d | 2023-12-13 |  |  |  |  | Upcoming | Ok | Stakeholder and social safeguards
O | Stakeholder consultations | Task | Upcoming | TBD | 17 | 2023-12-14 | 10d | 2023-12-27 |  |  |  |  | Upcoming | Ok | Stakeholder and social safeguards
O | FPIC process | Task | Upcoming | TBD | 18 | 2023-12-28 | 2d | 2023-12-29 |  |  |  |  | Upcoming | Ok | Stakeholder and social safeguards
O | Community consultations | Task | Upcoming | TBD | 19 | 2024-01-01 | 5d | 2024-01-05 |  |  |  |  | Upcoming | Ok | Stakeholder and social safeguards
O | Draft of governance structure | Task | Upcoming | TBD | 20 | 2024-01-08 | 3d | 2024-01-10 |  |  |  |  | Upcoming | Ok | Stakeholder and social safeguards
check | Technical Assessment | Workstream | Upcoming | TBD | 4 | 2023-12-04 | 25d | 2024-01-05 |  |  |  |  | Upcoming | Ok | TNC Feasibility workplan
check | Methodology | Sub-Workstream | Upcoming | TBD |  | 2023-12-04 | 10d | 2023-12-15 |  |  |  |  | Upcoming | Ok | Technical Assessment
O | Carbon methodology choice and review applicability | Task | Upcoming | TBD |  | 2023-12-04 | 5d | 2023-12-08 |  |  |  |  | Upcoming | Ok | Methodology
O | Gather information for baseline scenario and additionality | Task | Upcoming | TBD |  | 2023-12-04 | 10d | 2023-12-15 |  |  |  |  | Upcoming | Ok | Methodology
O | Methodology selection, criteria and needs | Deliverable | Upcoming | TBD |  | 2023-12-04 | 10d | 2023-12-15 |  |  |  |  | Upcoming | Ok | Methodology
O | Methodology selected | Milestone | Upcoming | TBD | 26 | 2023-12-15 | 0 | 2023-12-15 |  |  |  |  | Upcoming | Ok | Methodology
check | GHG Benefit and Carbon Accouting | Sub-Workstream | Upcoming | TBD |  | 2023-12-18 | 15d | 2024-01-05 |  |  |  |  | Upcoming | Ok | Technical Assessment
O | Literature review of carbon stocks | Task | Upcoming | TBD | 23 | 2023-12-18 | 2d | 2023-12-19 |  |  |  |  | Upcoming | Ok | GHG Benefit and Carbon Accouting
O | Spatial analysis | Task | Upcoming | TBD | 23 | 2023-12-18 | 5d | 2023-12-22 |  |  |  |  | Upcoming | Ok | GHG Benefit and Carbon Accouting
O | Geographical Boundaries | Task | Upcoming | TBD | 30 | 2023-12-25 | 3d | 2023-12-27 |  |  |  |  | Upcoming | Ok | GHG Benefit and Carbon Accouting
O | Carbon accounting (Baseline, Project, Leakage, Reversal) | Deliverable | Upcoming | TBD | 31 | 2023-12-28 | 7d | 2024-01-05 |  |  |  |  | Upcoming | Ok | GHG Benefit and Carbon Accouting
check | Financial Analysis | Workstream | Upcoming | TBD | 4 | 2023-12-04 | 53d | 2024-02-14 |  |  |  |  | Upcoming | Ok | TNC Feasibility workplan
O | Calculate Start-up investment | Task | Upcoming | TBD |  | 2023-12-04 | 5d | 2023-12-08 |  |  |  |  | Upcoming | Ok | Financial Analysis
O | Review possible funding sources | Task | Upcoming | TBD |  | 2023-12-04 | 3d | 2023-12-06 |  |  |  |  | Upcoming | Ok | Financial Analysis
O | Gather all the expected project costs | Task | Upcoming | TBD |  | 2023-12-04 | 5d | 2023-12-08 |  |  |  |  | Upcoming | Ok | Financial Analysis
O | Calculate carbon and non-carbon revenues | Task | Upcoming | TBD | 32 | 2024-01-08 | 5d | 2024-01-12 |  |  |  |  | Upcoming | Ok | Financial Analysis
O | Prepare Financial return Model | Task | Upcoming | TBD | 37 | 2024-01-15 | 5d | 2024-01-19 |  |  |  |  | Upcoming | Ok | Financial Analysis
O | Run different scenarios for carbon price | Task | Upcoming | TBD | 38 | 2024-01-22 | 2d | 2024-01-23 |  |  |  |  | Upcoming | Ok | Financial Analysis
O | Plan a long therm financial mechanism | Task | Upcoming | TBD | 39 | 2024-01-24 | 4d | 2024-01-29 |  |  |  |  | Upcoming | Ok | Financial Analysis
O | Financial analyst | Deliverable | Upcoming | TBD | 40 | 2024-01-30 | 12d | 2024-02-14 |  |  |  |  | Upcoming | Ok | Financial Analysis
O | Financial analyst complete | Milestone | Upcoming | TBD | 41 | 2024-02-14 | 0 | 2024-02-14 |  |  |  |  | Upcoming | Ok | Financial Analysis
check | Report | Deliverable | Upcoming | TBD | 27, 42 | 2024-02-15 | 24d | 2024-03-19 |  |  |  |  | Upcoming | Ok | TNC Feasibility workplan
O | Prepare Draft Feasibility Report | Task | Upcoming | TBD |  | 2024-02-15 | 15d | 2024-03-06 |  |  |  |  | Upcoming | Ok | Report
O | First report ready | Milestone | Upcoming | TBD | 44 | 2024-03-06 | 0 | 2024-03-06 |  |  |  |  | Upcoming | Ok | Report
O | Present feasibility report | Task | Upcoming | TBD | 45 | 2024-03-07 | 1d | 2024-03-07 |  |  |  |  | Upcoming | Ok | Report
O | Review suggestions | Task | Upcoming | TBD | 46 | 2024-03-08 | 3d | 2024-03-12 |  |  |  |  | Upcoming | Ok | Report
O | Finalized reviewed feasibility report | Task | Upcoming | TBD | 47 | 2024-03-13 | 5d | 2024-03-19 |  |  |  |  | Upcoming | Ok | Report
O | Final report ready | Milestone | Upcoming | TBD | 48 | 2024-03-19 | 0 | 2024-03-19 |  |  |  |  | Upcoming | Ok | Report
check | Wrap up | Deliverable | Upcoming | TBD | 49 | 2024-03-20 | 3d | 2024-03-22 |  |  |  |  | Upcoming | Ok | TNC Feasibility workplan
O | Next steps and timeline | Task | Upcoming | TBD |  | 2024-03-20 | 1d | 2024-03-20 |  |  |  |  | Upcoming | Ok | Wrap up
O | Organize and share deliverables | Task | Upcoming | TBD |  | 2024-03-20 | 3d | 2024-03-22 |  |  |  |  | Upcoming | Ok | Wrap up
O | End date | Milestone | Upcoming | TBD | 52 | 2024-03-22 | 0 | 2024-03-22 |  |  |  |  | Upcoming | Ok | Wrap up
Carbon Toolkit © 2024 by The Nature Conservancy is licensed under CC BY 4.0

## Summary
Project Goal | #UNPARSEABLE
Phase Number | TBD
Why This, Why Now? Situation | Enter WTWN Situation on Sheet Summary of A. Outline/B. Workplan Sheet
Why This, Why Now? Complication | Enter WTWN Complication on Sheet Summary of A. Outline/B. Workplan Sheet
Why This, Why Now? Resolution | Enter WTWN Resolution on Sheet Summary of A. Outline/B. Workplan Sheet
Scope | Enter Scope on Sheet Summary of A. Outline/B. Workplan Sheet
Project ID
Department
Desired Outcomes (10 Years) | Enter Desired Outcomes on Sheet Summary of A. Outline/B. Workplan Sheet
Key Intermediate Results (5 Years) | Enter Key Intermediate Results on Sheet Summary of A. Outline/B. Workplan Sheet
Strategy
Strategic Pillar or Foundational Function
Portfolio
Start Date | 2023-12-01
End Date | 2024-03-22
% Planned Work Complete | #DIVIDE BY ZERO
% of Time Left | 289.3%
Number of Action Items | 0
Completed | 0
In Progress | 0
Needs Attention | 0
Number of Working Days Left | 233
% of Deliverable complete | 0%