## Toolkit Database
| POC/Tool Owner Approval | [11 empty] | Open Source Checklist-Blaire |  |  |  | Yes-allow it to be editable
| 1. Anything missing? Please add. Anything incorrect? Please fix. |  |  | 2. Please check. |  |  | 3. Are there additional POCs that need to be reached out to regarding ownership of this tool, if yes, please contact them for approval and recognition and document that here | Data Validation | 4. License for Tool: https://chooser-beta.creativecommons.org/ | 5. Derivative works | 6. IS THIS TOOL OPEN SOURCE READY?-Type Yes-ready No-in progress No-Open Source N/a | ANYTHING TO NOTE? | Comms Approved? | Licensing agreement chosen? | POC approved? | Data Validation, CC | No-it should not be edited
Theme | Tool | Phase | Priority | Tool Owner and POC | Intended Audience | General Use Instructions | Tool Co-Owners & Contributers and approval date xx/xx/xxxx | Yes-Open Source Ready | Use the tool above to determine which license, if any, your tool needs. Select from the dropdown list | Should this tool be made editable for users to create their own versions? | Status | Notes |  |  |  | Creative Commons | N/A
Project Development | Feasibility Template | Feasibility | very high | Angela |  |  |  | No-In progress | [7 empty] | CCO1.0
Project Development | Template for a general validation/verification work plan/ tracker | Feasibility and PDD | high | Angela |  |  |  | No-Open Source N/A | [7 empty] | CCBY4.0
Project Development | Risk Assessment tool | Feasibility and PDD | medium | Angela | [11 empty] | CCBY-SA 4.0
C account | Dashboard Annual deforestation REDD | PIN and Feasibility | very high | Angela | 2022-02-17 | [10 empty] | CCBY-ND 4.0
C account | Annual carbon removals from restorations (Removals) | PIN and Feasibility | very high | Angela | [11 empty] | CCBY-NC 4.0
C account | Estimation of annual deforestation and emissions avoided - REDD (spreadsheet - Emiss Avoid) | PIN and Feasibility |  | Angela | [11 empty] | CCBY-NC-SA 4.0
C account | Restoration mapping and database (Single Platform/ Portal da Mantiqueira) | PDD | medium | Angela + Edson |  |  | Not a tool, a platform | [8 empty] | CCBY-NC-ND 4.0
| Potential new ARR tool |  |  | Angela anmd STefanie Simpson? |  |  | Check with Angela on this one???
Project Development | Carbon Project Manual Guidance for regions on the project development process (e.g., Blue Carbon Guidance) | Feasibility and PDD | high | Blaire (Diego)
Project Development | Database of Carbon Certification and Methodology | PIN | medium | Blaire (Diego) |  |  | Is this still useful?? Dont need to publish
Communication | Communication Template (factsheet) about the project | PIN and Feasibility | high | Blaire J. Langston (TBC)
C account | IFM (ACR) decision tool to assess the baseline | PIN and Feasibility | very high | Cat |  |  | internal tool for BOE
Financial | Carbon Price forecast and market status | PIN and Feasibility | high | Check Kim (TBC from Trove) |  |  | internal
Policy | Guidance for countries on A6 and market implementation that aligns with NDCs/avoids double counting (e.g., The Bahamas guidance) | PIN and Feasibility | high | Check with Kim (TBC) |  |  | Check with Kim
Policy | Country Specific Carbon Policy Status (NDC, Registry, carbon rights Legislation…) | PIN and Feasibility | medium | Check with Kim (TBC) |  |  | Check wiht Kim
Project Development | TOR / RfP for feasibility assessment and criteria for assessing proposals | Feasibility | high | Diego |  |  | Internal
Policy | Framework to assess standards | Feasibility | very high | Diego |  |  | Internal
Project Development | TOR / RfP for VVBs and criteria for assessing VVB proposal | PDD | high | Diego |  |  | Internal
Project Development | TOR / RfP for PDD developers and criteria for assessing proposals | PDD | high | Diego |  |  | Internal
Project Development | Guideline to pipeline list the project in VERRA | PDD | very high | Diego |  |  | External
Project Development | Project Idea Note template and assessment scoring | PIN | very high | Fabiano |  |  | Assessment scoring is Internal (for NCSA), PIN can be external
C account | Soils Revealed-LINK TO WEBSITE IS OPEN SOURCE? | PIN | very high | Food Syst (Stephen Woods)
C account | Sampling selection-LINK TO WEBSITE IS OPEN SOURCE? | PIN and Feasibility | very high | Food Syst (Stephen Woods)
C account | Risk Map and allocation tool based on JNR rules (GEE script/ distance to deforestation) TCC | PIN and Feasibility | very high | Hayden |  |  | Maybe not publishable, needs more thought or discussion? Not sure if Hayden finished
| Ex-ante tools for REDD |  |  | Hayden--is Angela POC? |  |  | ??
C account | Automated US National Forest Inventory data summary tool (using TreeMap spatial query/FIA similar plot query | Pre feasibility & Feasibility | high (for US) | John |  |  | Not sure
Legal | Grant Agreement Models for Accelerator | Feasibility and PDD | high | JR
Legal | Updated Roles and Legal Coverage | Feasibility and PDD | high | JR
Legal | Prezi/Wiki | Feasibility and PDD | high | JR
Legal | Nature of Carbon Rights | Feasibility and PDD | high | JR
Legal | Advisory Document for Working with Companies | Feasibility and PDD | very high | JR
Legal | Advisory Document for Commodities Issues | Feasibility and PDD | very high | JR
Legal | Carbon Credit Transfer Agreements (Spot and Forward) | PDD | very high | JR
Legal | Retirement Agreements | PDD | very high | JR
Legal | Carbon Transfer & Retirement Term Sheets | PDD | very high | JR
Legal | Example Agreement Library | PDD | very high | JR
| Carbon Markets Social Risk Assessment |  |  | Rane
Social | Mapping Interested Parties | Feasibility and PDD | high | Rane
Social | Stakeholder Engagement and FPIC Process guide for carbon projects | Feasibility and PDD | high | Rane
Project Development | Guidance for community engagement – (e.g., Human Rights Guidance, developing CIRCLE program) | Feasibility and PDD | medium | Rane
| Governance Structures for Carbon Projects |  |  | Rane
Social | Guide to assess capacity on the ground | Feasibility and PDD | very high | Rane
Social | Benefit sharing principles and guidance | Feasibility and PDD | very high | Rane
Social | TORs for legal agreements with communities- Expression of Interest & Project Implementation agreement | Pre feasibility & Feasibiliyt | very high | Rane
Financial | Pre-feasibility model that includes cost categorization | PIN | very high | Rob
Financial | Financial model (cost/revenue – cash flow) | PIN and Feasibility | very high | Rob
Feasibility | Ex-ante ARR estimation - TerraCarbon | PIN and Feasibility | high | Angela, Fernando
C account | GIS solution for additionality and ex-ante assessment using ARR proxy areas TerraCarbon | PIN and Feasibility | high | Angela, Fernando
C account | Leakage estimation tool for ARR projects | PIN and Feasibility | high | TC + Angela, Fernando
C account | Annual carbon removals from Soil for grassland restoration and regenerative agriculture | Feasibility | very high | Jacob finished? |  |  | Check if this is uploaded
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: should we make a tool for census based? Reply: also, maybe include emission factors for soil, dead wood and others
Note on B42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: There are a number of tools that should be linked to this, but shouldn't necessarily be provided as standalones - they are linked in the document
Note on B45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I don't have a tool to do this and don't plan to make one
Note on B46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: All we have right now is the benefit sharing report, which is public
Note on B47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is not standalone- should be linked to stakeholder engagement and FPIC guide (and there are a number of other associated tools)

## CM Toolkit (hidden)
Carbon Markets ToolKit
Theme | Tool | Phase | Status | Priority | Notes
Project Development | TOR / RfP for feasibility assessment and criteria for assessing proposals | Feasibility | not started | high
Legal | Grant Agreement Models for Accelerator | Feasibility and PDD | in progress | high
Legal | Updated Roles and Legal Coverage | Feasibility and PDD | in progress | high
Legal | Prezi/Wiki | Feasibility and PDD | in progress | high
Legal | Nature of Carbon Rights | Feasibility and PDD | in progress | high
Project Development | Guidance for regions on the project development process (e.g., Blue Carbon Guidance) | Feasibility and PDD | in progress | high
Social | Stakeholder mapping and engagement process | Feasibility and PDD | not started | high
Social | FPIC process guide for carbon projects | Feasibility and PDD | not started | high
Project Development | TOR / RfP for VVBs and criteria for assessing VVB proposal | PDD | not started | high
Project Development | TOR / RfP for PDD developers and criteria for assessing proposals | PDD | not started | high
Baseline | GIS solution for additionality assessment using ARR proxy areas TerraCarbon | PIN and Feasibility | not started | high
Baseline | Leakage estimation tool | PIN and Feasibility | not started | high
Communication | Communication Template (factsheet) about the project | PIN and Feasibility | not started | high | suggestion received during the CoP meeting
Financial | Carbon Price forecast and market status | PIN and Feasibility | not started | high | [CL- Suggest low priority]; KM - This resource will be available through Trove as early as December, funded by Corporate Engagement
Social | Guide to assess capacity on the ground | Feasibility and PDD | not started | high
Social | Benefit sharing principals and guidence | Feasibility and PDD | not started | high
Social | TORs for legla agreements with communities- Expression of Interest & Project Implementation agreement | Pre feasibility & Feasibiliyt | not started | high
Project Development | Template for a general validation/verification work plan/ tracker | Feasibility and PDD | in progress | medium
Project Development | Risk Assessment tool | Feasibility and PDD | in progress | medium
Social/Project Development | Guidance for community engagement – (e.g., Human Rights Guidance, developing CIRCLE program) | Feasibility and PDD | not started | medium
Baseline | Restoration mapping and database (Single Platform/ Portal da Mantiqueira) | PDD | in progress | medium
Project Development | Database of Carbon Certification and Methodology (in progress) + Guide for selecting the most appropriate methodology | PIN | in progress | medium
Policy | Country Specific Carbon Policy Status (NDC, Registry, carbon rights Legislation…) | PIN and Feasibility | not started | medium | KM - Resource will be available as early as December through Trove (seat holders will tentatively be Kim (for ICP team), Blaire (for the field), and Andrea (for the Accelerator))
Policy | Guidance for countries on A6 and market implementation that aligns with NDCs/avoids double counting (e.g., The Bahamas guidance) | PIN and Feasibility | not started | medium
Project Development | Feasibility Template | Feasibility | in progress | very high
Legal | Advisory Document for Working with Companies | Feasibility and PDD | complete | very high
Legal | Advisory Document for Commodities Issues | Feasibility and PDD | complete | very high
Legal | Corresponding Adjustments (with Policy Team) | Feasibility and PDD | in progress | very high | KM - is this referring to the general explainer on CAs? Or specific country overviews of CAs? (the former is nearly finalized, the latter doesn't exist yet but could be available through Trove, I assume)
Legal | Carbon Credit Transfer Agreements (Spot and Forward) | PDD | complete | very high
Legal | Retirement Agreements | PDD | complete | very high
Legal | Carbon Transfer & Retirement Term Sheets | PDD | complete | very high
Legal | Example Agreement Library | PDD | complete | very high
Project Development | Project Idea Note template and assessment scoring | PIN | complete | very high
Baseline | Annual carbon removals from restorations (in progress) same question as above | PIN and Feasibility | in progress | very high
Baseline | IFM (ACR) decision tool to assess the baseline | PIN and Feasibility | in progress | very high
Baseline | Risk Map and allocation tool based on JNR rules (GEE script/ distance to deforestation) TCC | PIN and Feasibility | in progress | very high
Baseline | Annual carbon removals from Soil for grassland restoration and regenerative agriculture | PIN and Feasibility | not started | very high
Financial | Cost Categorization spreadsheet | PIN and Feasibility | in progress | very high
Financial | Financial model (cost/revenue – cash flow) | PIN and Feasibility | in progress | very high
Baseline | Annual deforestation loss and emissions - REDD |  | in progress | very high
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Would it be useful to have a column for point of contact?

## Data Validation (hidden)
Yes-Open Source Ready
No-In progress
No-Open Source N/A